## Submittal Register
No | Document Title | Status | Revision | Discipline | Area | Due Date | Approved Date
SR-001 | HVAC Ductwork Shop Drawing | Submitted | Rev 2 | Mechanical | Generator Room | 2026-03-01
SR-002 | Generator Base Frame Detail | Under Review | Rev 1 | Structural | Generator Room | 2026-03-05
SR-003 | Fire Rating Certification | Approved | Rev 3 | Fire Protection | Generator Room | 2026-02-15 | 2026-02-28
SR-004 | Ductwork Pressure Test Report | Submitted | Rev 1 | Mechanical | Level 2 | 2026-03-10
SR-005 | Exhaust Fan Installation Guide | Rejected | Rev 0 | Mechanical | Rooftop | 2026-03-12